## Sheet1
0
LTI_AZL_22-01-12_EC_OB_Success Factors OLC ATM - Manager USERID is fetching NO_MANAGER when there is no manager listed eventhough the condition is not stated in FS
LMS : Option 'Learning' not visible under 'Home'
LTI_AZL_26-02_18_EC_OB_SendWordNow_Day2_T0018_CUSTOM VALUE 4 - Data issue
Processing of data in HR Feeder fails
LTI_AZL_ServiceNowUI: The field 'Cancel Comments' is not present. The user is not prompted to enter any comments when the request is being cancelled.
LM did not receive probation period alert notification
LTI_AZL_26-02_26_EC_OB_SendWordNow_Day2_T0026_EMAIL 1 - Outbound file and report out of EC do not match for Email 1 field when using the same business rule
Verify landlord insurance policy and be modified
SIT3 - WFA_Day2_T0250_externalCode
INT007_Quality_Resource_Group_Phone Number mapping change
Cancelled LOA is not shown in History of Job information
Suffix Value not replicated
AZIND004_HRDB EE_wrong Legal Entity
AZIND004_HRDB_EE - Manager ECID
COE didnt receive approval mail for promotion 16 and above
Unabe to select SGP position in LM field while creating position
LTI_AZL_11-02-12_EC_OB_Sailpoint_Job Title is picking data from Job Title instead of name(Position FO)
List of Banks are not filtered and error on Selecting the bank
ECPth_Apptio_CCYYMMDDHHMMSS.csv - Mgrclock transformation not working as expected
Email List Automation: File name used is not matching with requirement. Temp word is missing
ServiceNow UI - The field should '% increase' allow ony 2 decimal places but it allowes more than two
SIT3 - Psoft Financial_Day2_T0013_terminationdate
Holding Division Appears under the "Manage Data" section in the Admin Center not the "Manage Organisation, Pay and Job Structures"
SIT2-EC-OB-Service Now-Header Record is missing from the file.
SIT_1 EC: Fehlerhafte Anzeige der Kacheln
Login issue
no ending pipe in record type 3 rcipsoft
Modifications to Names are not Showing up in the EC Search by Name List
SIT3 - WFA_Day2_T0283_variable_comp_external_name
There is no field "Record Completions" below the "Action" section
On Changing the Employee work data LM and HRBP not receiving notification
Script Error - LM vs HRS
Some reports not found
The "Search for Items and Curriculum" tile is shown already, I don?t need to click on the "Next" button. If I click on "next" a reminder pops up saying to select an item/curriculum first.
Employee did not receive notification for personal data change
Translation of Survey
Enriched_ServiceNow - There is no value mentioned in the FS under Field Label (Used for Header Record) for Employee ID
Verify that bonus payout feature is correct
SIT2-EC-OB-HR WFA-(B) Is Primary: Getting False value even though Business Email is present and its primary.
Not able to save bank info
iled 50 and 51 of record type 1
SIT2-DVFS-Selection Criteria: Only Active records are coming in file. Requirement clarification needed
No Add button for Delegation
Target LM did not receive Notification
INT010_VolunteerMatch_Terminated Employee Logic change
HRS-38aWithinDepartmentGrade13to15 - Did Not Interpret As Lateral but Data Change
EC-OB-DVFS-Initial Load-File Name: Preifx AZL029 added to the file name which it should not.
"Search for actions or people" search bar not available;
Able to save invalid numbers
Title "Bankverbindungen" not available
016-016-AZ SE Active Directory - BusnPhone , not including the area_code.Clarify if its business mobile / business landline .
HR WFA - WFA_Day1_T0093_manager-category is not working
SIT2-EC-OB-Actimize-Selection Criteria-Inpatriate records are not populated in file. Records not present in error report.
35d - Documentation Mismatch
Payroll:Item:Gender
INT016-AZSE Active Directory - PersonaIid field mapped to custom-string9 and field is marked as"Required".the interface need to includes non-employees who might not have payroll id
no fields tu fill in
Kachel "Team-Zusammenfassung" nicht vorhanden
all
Postadresse wird nicht an SAP geliefert PerNR 99803360
Error Message poped up after clicking on search
LOA Start & end date not visible under Job information of employee
HRDW_MAIN.Employment_Info: ELIGIBLE_FOR_STOCK coming as "0" instead of Trure/False(0/1)
There are no courses available
Newly created record not pulled in the extract file- CybershiftUserprofile though matching the criteria.
FMInteract - The translation rule is not working properly for the field 'Payroll_ID'
Datumänderung nicht möglich
DVFS: Duplicate records are present in the interface file.
SIT2-EC_OB_QRG_Day1_T0010_MAIL_CITY: Data is not coming from Corporate City field
HRDW: Global Assignment table displayed 4214 record moved to table even though we don't have data for the global assignment columns
Search not working due to user account fault
Payroll:Item:Grade Code
Verify terms and conditions section
SIT2-EC-OB-SFOLCATM-Status: Included Terminations from more than past 10 days from run date.
LTI_AZL_03_ServiceNow_T0032_Verification of Email - ServiceNow - The email notification to the first Approver has wrong Email Header
Duplicates present in the file - ECArc_Kenexa_20170721151654
SIT3 - WFA_Day2_T0248_vacant
Verify new merchant addition
Verify auto upgradation feature
SIT2-EC-OB-HR WFA-Terminated record is displayed in file. As per Business requirement, it should include only Current, New Hire OR Rehire - Employees or Non-employees with future dated data too
HRS able to change their own position and manager
EC Config
Employee can view Purpose field under bank info
Employing Unit - BoardUnit - Department - CC - Loaction Mapping is not there
Org Chart UI- Fields Company, Division,Department, Cost Center, Line Manager, Position Title - cases should be maintained as is in file
FM Interact:: Incorrect Error Report : Employees have hiredate, but the records errored out with message "Error in the field [Current_Hire_Date] for the Employee:"
Please check Description of Testcase
EC_OB_ECPth_AZLAD - ipPhone is not populating area code
ServiceNow UI - Unable to fetch position request details using SAOP UI. Eorror message is being displayed.
Genehmigung durch HRS erforderlich bei Angabe Auslandsüberweisung und Bank aus Deutschland
NUll pointer Exception
No email received.
Fälligkeitsdatum Begriff ist unpassend
LTI_AZL_06-02-06_EC_OB_UPS Trackpad_Day2_T0006_CostCenter - Cost Center data in Outbound file is not matching with Cost Center data in EC
EC_OB_ECPth_AZLAD - lot of records in the error report since Manager field is marked as 'required'
Can't login
SIT2-EC-OB-SAP eRecruiting-Org units file-Business Unit/Board unit that has Amosa as Employee Entity is displayed in Org Units file 1.
Payroll: NewJoiner
HRDB_EE-Role missing
SIT3 - WFA_Day2_T0280_referral_external_name
LOA Issue
Warnhinweis ein ausgewähltes Element ist bereits mit einer anderen Umfrage verknüpft, dies ist allerdings nicht korrekt
Email List Automation - There is no data in the HRADM.EMAIL_DIST_LIST_EXCEPTIONS table.
SIT2-EC-OB-ADP-EMPLID-Not displayed for all the records even though its required
Line Manager sagt Maßnahme für MA ab: unverständlicher 2. Warnhinweis
HRDW_MAIN.Emergency_Contact: Displays "0" instead of True
SIT2-EC-OB-SAP eRecruiting Employee1-Birthdate is missing from the file even though records have data in UI.
Email List Automation - The file is expected to have just 28 email addresses of supervisors but in actual the file is pulling 213 records with non supervisor email addresses as well
Payroll:Item:P.F. Registration Code
Keine Schaltflächen zum Schliessen des Fensters
ServiceNow UI - There are two 'My self service' menu in the homepage for Melania Meyer only
unable to enter any values in 'New Target Total Direct Compensation'
ADP employee demographic rcipsoft
HRS not able to change history of Job Info
Kundenindividueller Status Vorruhestand fehlt in SAP
Manager is able to see scorecard
LMS : Item not viewable
LTI_AZL_03_ServiceNow_T0044_Verification of Email - in HRBP email notification, the body of the email begins with the word "Body"
LMS: Approval Step Missing
HRBP-33cManageLayOffs_Approval
Change of Compensation Info is possible for LM
SIT_1_EC: Fehlerhafte Anzeige der Kachel DEÜV
After the LOA submission, details of the employee status is wrong in Job information
Double enteries in the Job Info table after manager_id event change
Org Chart - made updates to fields to be optional
LTI_AZL_03_ServiceNow_T0004_UserInterface - User is seeing more PRs than their own
SendWordNow : PHONE 3 field not populated with phone number. instead its populated with 1
Verify response time is as expected
HRDW_MAIN.JOB_INFO: IS_FULLTIME_EMPLOYEE displaying "0" for True and False.
LTI_AZL_ServiceNowUI_Day1_T0069_Verify that the appropriate roles are able to decline modify position requests - HRBP is unable to decline a Employee Change in Position PR
Payroll:Item:Occupation Code
SIT2-EC_OB_HRReporting_WFA_Day1_T0060_company: Company MA0008 is displayed which is not valid value expected in that field.
LMS : Return to Curriculum option is not visible
DVFS: Primary_name_effdt field is pulling data from 'effective as of date' instead of 'last_modfied_on'
SIT2-EC-OB-SAP eRecruiting Employee1-Header record-First name and Last name doesn't have space inbetween
CONVERSION Instance: HRDW_MAIN.POSITION_DETAIL: HR WFA: Corporate State is not displayed in 2 fields in HR WFA file
Position Cluster displaying a Dash
Payroll:Item:UAN
approval needed
SIT2-EC-OB-HR WFA-State-Corporate Address-State is not displayed in file even though we have address set in UI under FO.
Verify legal policy module changes
ServiceNow UI - Comp team member is able to 'Assign Recruiter'. It is expected that only Tracy should be able to assign recruiter.
SIt2-EC_OB_HRReporting_WFA_Day1_T0104_timeInJob: Data not displayed for this field in file for all records.
New Hire Issue - After Completing New Hire, Records Appear Differently When Accessing via Search (typing in name)
Disbility field available for LM
Service Now UI " Word Position is spelled incorrectly"
ServiceNow UI - When a position request is in the status 'Pending Approval' Tracy is still able to edit the form and assign recruiter.
Employee did not receive notification for Work Eligibility
FM Interact - Required fields are mapped but defaulted to null. Since its marked mandatory, records are not pulled by interface.
Admin Center not available
ADP-20170727 21:04:23 file-Job Record and Employee Data Record counts are not matching
SIT3 - WFA_Day2_T0223_cust_Pay_range_Frequency
Test different methods of routing
ServiceNow application does not allow the HR Comp person to use "Permanent" as a valid Employee Status - hangs the system
LTI_AZL_22-01-32_EC_OB_Success Factors OLC ATM - For many records Manager Category <> People Manager but still ithe field 'people manager; populating as 'yes'
HRS 63A: Add Non-Employee Referral Code to Non-Employee Record
EC_OB_Day1_AZLife Orgchart: EmployeeEmployeeType: When Employee Class is Intern, we are not getting "EmployeType" as "Employee"
Copy of an SO had different amount of days than the original
The pop-up window "Please confirm your request" did not appear.
HRS61-Change/Add SalesCompPlan
Not able to find test scenarios- Job & comp infor missing for LM & HRS
Delivered Corrupted file- ECPth_CybershiftElement_20170714121916. Unable to open the file in excel/notepad/ultraedit
Unable to save the new employee as it is asking to provide the bank number which is not a mandatory field
Unable to add a new Holding Division as admin "rakins"
Field not shown
HOST ADRESS kommt nicht in SAP GUI an !!!
"Budget increase" window apperas but all amounts equal 0, so that no increase is possible.
MFT: Onbase - No file in MFT Inbound/Archive location for 15sep
SIT2-EC_OB_HRReporting_WFA_Day1_T0251_name: Data is not populated from UI to File
SIT3 - WFA_Day2_T0284_variable_comp_start-date
LMS :Warning Page - On the Warning Page there is no Button for "Yes" only a Button for "Cancelling the report"
ServiceNow UI - Tracy is able to view one draft request under 'Position request my tasks'.
Language of Instructor Notifications
SIT3 - WFA_Day2_T0225_cust_Pay_Range_Mid
Unable to view position as the HRBP in the Position Org Chart
Wording of "Warnhinweis" to be modified to "Hinweis"
Success Factors OLC ATM - Duplicate record found
SIT2-EC-OB-Actimize-Day1: New hire entered on 7/12 is not included in the file generated.
SIT2-EC-OB-GIAM ID-Externla Company Name Field-Non Employee Referal/External Name is not displayed in UI to validate the field in file.
EC-OB-DVFS-Initial Load-Preferred Field-Transformation rule is not working as expected from source to target file
SIT2-EC-OB-ADP-Demographic- Not displaying File Number even though it's required field
Employee - RBP - Position Org Chart Visability - Please update script
LTI_AZL_ServiceNowUI: Update button is not working as expected
LTI_AZL_ServiceNowUI_Discrepencies with the finance consultants name
LTI_AZL_03_ServiceNow_T0003_UserInterface - Hover over text is missing for required fields
Enriched_ServiceNow - There is no value for cube location in the enriched file. The column is entirely blank.
LTI_AZL_29-02-01_EC_OB_UPS Trackpad_Employee Class - Some EEs appear to be missing from the Outbound file that DO appear in EC and follow the Business Rules
Gaps in test scenario description?
ADP emmployee data rcipsoft dup record
LTI_AZL_26-02_21_EC_OB_SendWordNow_Day2_T0021_PHONE 1 - Outbound file record count and report from EC record count does not match
No Permission to create position
SIT3-INT013 Service Now: Update extract logic for existing EMPLID field to populate the PSoft Legacy ID (Biographical Information.custom-string8).
Search is selective for language
SIT2-EC_OB_HRReporting_WFA_Day1_T0025_isAddSameAsEmployee: Emergency Contact Address flag not populated
ServiceNow UI - Unable to look up requests as hiring manager and cancel the same.
INT008_Rivermine_mapping change for preferred name
Address Change - The field "District" is not available.
LOA start date and return date not present in teh Job information section
INT010_VolunteerMatch_mapping change for preferred name
Interim Grade Field - Not editable by HRBP
SIT2-EC-OB-HR WFA-Email Address(B)-Not displaying the correct email address for the record.
HRDW_MAIN.Emergency_Contact: Records displayed in the table even when no emergency contact detail information exists.
Unable to see add option in personal information for creating ethnicity
Payroll:Item:Permanent A/c No.
INT010_VolunteerMatch_Phone Number mapping change
SIT TC: Missing Step in Testcase
LM can see the employees bank details
LMS : Learning proposal link missing
LMS : there is no available course date
SAP eRecruit - One Inpat record which meets all the selection criteria is not showing up in the interface file.
Fehlerhafte Abgrenzung der SAP-Infotypen 0000 und 0001
LTI_AZL_03_ServiceNow_T0002_UserInterface - Conflicting messages on ServiceNow when deleting job descr. / attachments after a user Submits on first page
Success Factors OLC ATM - The file isn't pulling retro records (terminated > 10 days before but updated in EC < 10 days in the past)
01-14-01 HRS-OETransfer
HRBP not able to view Position Grade or Job Code
Keine Übersetzung für "External Training Request" + "Learning Proposal" (unter Startseite-Schulung -> Verknüpfungen) sowie die Seiten dahinter!
Kursleiter
HRS-63A:
LMS - No option to withdraw from course
In record type type the User 2 Char field is limited to 30 rcipsoft
MFT : HR WFA -No file in MFT Inbound location for 13, 14th and 15sep
Barzahler konnte ausgewählt werden
Different field names in hiring action and position object
LTI_AZL_26-02_20_EC_OB_SendWordNow_Day2_T0020_PHONE COUNTRY CODE 1 - this custom field is not following the business rule & not populating correctly
LTI_AZL_03_ServiceNow_T0013_Verification of Email - ServiceNow - text in email is different from requirements
SIT TC
LTI_AZL_01-02-06_EC_OB_Actimize - 1 employee has a Salutation of a number in EC, but "Dr." as Salutation in outbound file
INT016_AZ_SE_Active_Directory_mapping change for preferred name and header
HRDW_MAIN: Position: Vacant: Displayed ?0? for True and False values
AZLAD - For one of the header field, the FS has 'Jobcode' but the interface file has 'Jobcode Desc'. The field is actually mapped to externalname (Position). Please clarify if it should be 'Jobcode' or 'Jobcode Desc'
Org chart - Get visio diagram(hierarchy) not working from Google chrome. If any IE screens are open, then it opens the visio . else doesnot open.
SIT3 - WFA_Day2_T0222_cust_Pay_range_Currency
LMS : The said field is not visible
LM cannot able to terminate an employee
LTI_AZL_14-01-116_EC_OB_HRReporting_WFA_Day1_T0116_rel-user-id
LTI_AZL_22-01-31_EC_OB_Success Factors OLC ATM - translation rule for 'Employee type' is not mentioned in FS for terminated employees.
After data update through feeder cost center is not transferred
HRS-63AddSalesCompensationPlanNon-EmployeeReferral
Approval Tasks that are DECLINED / REJECTED via email using Good Declines the Task, but does not Cancel the PR
Not only "Admin Center" in dropdown
volunteermatch: default location setup missing for 8 entities
01-04-44 Incorrect Event/Event Reason on Transaction, No Popup Window, No Workflow
Meldung erscheint nicht.
Search not possible - without hits
SIT3 - WFA_Day2_T0277_position_loc_state
Manage Link Missing for HRBP
ServiceNow UI - When a modify position request is in 'Draft' status the comp team member is able to view and edit the entire form.
ServiceNow UI - Compensation team member is not able to view position request tasks assigned to the team
LTI_AZL_11-02-14_EC_OB_Sailpoint_Business unit name mapping issues
SIT3-ServiceNow-MobilePhone: Getting Business Mobile number instead of Home Mobile.
Verify that new shipment is created
SAPeRecruiting - The Employee file 2 is not pulling any records for Emp Class = Intern / Working Student / Trainee.
All mandatory fields are filled, but error message raises
SIT3 - WFA_Day2_T0249_description
01-13-16 HRS-JobChangeLateralMove
Only 2 reports show up - not five
LMS : no remove page
Felder "Dependents"
LTI_AZL_14-01-117_EC_OB_HRReporting_WFA_Day1_T0117_card-type
LTI_AZL_26-02_20_EC_OB_SendWordNow_Day2_T0023_PHONE 2 - Outbound file record count does not match with EC report for same business rule
Create Online Item - Drop down "item type" (DE: Elementtyp) does not offer "ONLINE COURSE"
SIT TC: Testfall nicht klar
MFT : FM Interact. Additional 4 files are present in the location generated on 9/13, other than expected file and 1 file dated 9/14. File name :Employee_20170914045650.csv.pgp &_20170~2. Refer attachment for more details
SIT TC: Grade not editable
There is no field for Interim Grade
SAP eRecruit - As per the FS the field 'BIRTHDATE' should not pull any values, it should populate only 'null' values. But the interface file has birthdates pulled from the UI.
Test to verify sales user authorisation
MFT: No file present for " ADP - Employee Demographics" in ADP Inbound folder. Latest file present was for11th sep
LTI_AZL_22-01-20_EC_OB_Success Factors OLC ATM_Day1 - EMPLID is directly mapped to Local ID with no translation rule.
The Recurring Absence Check Box is Greyed Out - Script needs to be updated.
Orgchart UI: when scrolling down the viso diagram, the search button displays over the org chart visio diagram
Warnhinweis ausgewähltes Element ist bereits mit einer anderen Umfrage verknüpft, es ist aber keine andere Umfrage verknüpft
LTI_AZL_26-02_27_EC_OB_SendWordNow_Day2_T0027_SMS 1 - Outbound file and EC report record counts don't seem to match using the same Business Rule and Entities
ServiceNow - Cancel notification email is not formatted according to the requirements
ServiceNow UI - An extra field 'Send for Approval' is present in the requestor form while I create a position request.
LMS - Scheduled classes issue
Only 3 instead of 4 Tabs displayed
Classification not available
Test Scenario description: Missing steps?
HRDW_Main: Position: POSITION_FTE: Displayed round off numbers instead of 2 decimals.-
Enriched Cybershift Userprofie : EmployeeEndDate - showing incorrect value. 22025-12-31 instead of 2025-12-31
Target LM notification
No Notification received for HRS for ChangeDisabilityStatus
LTI_AZL_ServiceNowUI: No notification/text is being displayed when a position request is submitted
Anlage SAP Infotyp 0000 darf nicht erfolgen
NPS Scale shows "6" twice instead of "8"
Language Mixture after switching the language from EN to DE
SIT1 : Infterface - Field {First Pay Date} Career file
No message displayed for dependent birth certificate, instead data saved successfully occured.
INT016 - AZSEAD - File generated with only one record.EcArc_AZSEAD_20170912113617
CR : If Employee Class = Contractor, Interface should not pick up the employee
SIT3-Servicenow-Emplstatus- Coming as "A" even for Dormant status. when employee is on Global Assignment at presnt.
ServiceNow UI - Tracy is able to assign recruiter but the status of the form is not being moved to 'Recruiter Assigned' even after close completing the task.
LTI_AZL_14-01-108_EC_OB_HRReporting_WFA_Day1_T0108_custom-string1
LTI_AZL_ServiceNowUI_Day1_T0100_Verify that the appropriate roles are able to provide proxy approval - Recruiter does not have permission to complete Approval Tasks on behalf of Approvers
Usability - Catalog Search - Filters
Translation of Complete Page
ServiceNow UI - Under the HR panel in the left there is a tab 'Position Request SLG Requests' which is the same for all the approvers/team. Probably it could be renamed to be generic.
Cannot Save without "Classification"
can't select course
various languages(English, German, French) appear on the website under "My Employee File"
Conversion File-HR WFA-Position field is coming as blank for 24 records.
Amex Concur - Record 310_Active field -For 3 records, N is populated , instead of default value Y
"Questionnare Survey" not visible
HRS does not have direct reports to change pay targets
HRS does not have direct reports to add pay targets
SIT2-EC_OB_HRReporting_WFA_Day1_T0105_timeInPosition: Data in this field is not coming for all records
Change of date when copying a position
rcipsoft keeps processing
Commerce icon is not showed
Missing Picklist for "Quelle"/ Source
WFA_Day1_T0049_company - Global Company is not mapped
LM not receiving workflow notification on Job Change (PT to FT, FT to PT)
LTI_AZL_29-02-01_EC_OB_Quality Resource Group_Employee Class - QRG - Not all INTERNS are coming into the Outbound file
Can't select employee
SIT3 - WFA_Day2_T0251_name
ServiceNow UI - API calls - The API call is expected to pull the HRBP Position ID (matrix relationship) but in actual it populates the original position ID itself.
SIT: AZLife Orgchart_Day2_T0006_EmployeeFirstName: Preferred name is moved instead of First Name
LTI_AZL_03_ServiceNow_T0036_Verification of Email - Email to Hiring Manager & Requestor has "New" in the subject and in the Body but should not
Not all fields are copied with "add peer position"
HRDW---PRE_PS_DATA need to be loaded in HRDWTST1
Fehler bei Eingabe einer Bank im Ausland
step useless
Verify that API response for M1 is correct
Position Management - Position ID
Item Creation: validation error
Item cannot be found - test case/description should be changed.
Please check Cancelation and Pricing Policies
LTI_AZL_ServiceNowUI : When the user is navigated to second page of the request form, a text is being displayed that position request is submitted wheras the request is not yet submitted
No Notification mail sent to the employee
HRBP didnt receive notification on Assigning LOA Paid & Unpaid
SIT3-GIAM SE ID_Day2_T0022_ID-TempDeactivationStartDate: Effective date is not reflected in the file for this field
Step 13 cannot be fulfilled, as there are no registrations
INT016-AZSE Active Directory "Personalid" mapped to payrollid field marked as Required. Non-Employee dont have Custom-string9, records move into error report.
Success Factors OLC ATM - The file isn't pulling any retired records.
Summary Defect for HR factory role permissions
Verify SQL injection is not happening
Enriched : Cybershift Userprofile - field "EmployeeLevel (col 1084-1133)" - truncated the first char of the string. Instead of Mgmt , its shows "gmt"
Search Bar Defect
Can not register any test-user
Org Chart UI -AZL Network ID should display all CAPITALS and "Type" field should display "Non-Employee" for Non-employee
SAP eRecruit - Header 'BIRTHDATE' is missing in the FS but present in the file.
Worksheets aren#t launched for Amina Lateef
When keying a term the option of what to do with direct reports is different
Enriched: Cybershift Userprofile :FOR Employee Belongs To Record : Record ending position shifted by one. Record ending position show as 107 instead of 106.
Popup-Fenster erscheint nicht
SIT2-EC_OB_HRReporting_WFA_Day1_Impat Scenario is not coming in the file
ServiceNow UI - Cancel comments field is editable for HRBP, only requestor should be able to cancel a request and will be prompted to enter cancel comments.
ServiceNow UI - Picklist to be removed from the approval task
AZLAD - Inpat records are NEITHER present in the interface file NOR in the error report.
Required permissions are missing to edit "Locations"
Verify that functionlity P is working as expected.
LTI_AZL_11-02-10_EC_OB_Sailpoint - Manager emplid is by default pulling person-id-external
SIT2-EC-OB-PSOFT: Data chage record populated for one scenarios but not for other.
Verify existing user re registration
Verify new role expiry feature
Retest
ServiceNowUI_A comp team member should be able to edit only a few API fields in the requestor form, currently the entire form is editable for a comp team member.
Translain Last Name
Can't choose "My employees"
Tab for Position Org Chart exists if User is Manager
HRDW_MAIN.JOB_INFO: FIR_AND_PROPER should be FIT_AND_PROPER
Replizierung aufgrund ausgelöster PeCoSys-Meldung nicht möglich
Rivermine Enriched file: FinancialApprover logic not correct, Doug/Tony to confirm the join condition to be used to derive the logic.
Black screen. Errrormessage
Translation Defects/ Sammeldefekt
no recommendation available
Org chart dewtails missing in the file
Link does not work
INT042_GIAM_Phone Number mapping change
Change Main Bank IBAN
LM - RBP - Position Mgmt - Position Grade & Job Code are visible to the LM.
SIT TC: No field "notice period"
Edit position option is not availabe for HRBP
SIT3-AZtek-Job Title from Fo Position Title, even though its present record is populated in error report as missing title.
Closed: CR 41-2018 Übersetzung Adresstypen
LMS - SIT
Payroll:Item:Marital Status
AZLAD - File is not found in the MFT Inbound location, but received error report for two consecutive days.
ServiceNow UI - Unable to change the status of the form when filled before close completing the task.
MFT : Enriched file: Org Chart- File not present for 14th adn 15th
Es öffnet sich kein Popup-Fenster. Man kommt gleich zurück zu "Persönliche Informationen".
Mistake in Test Process - wrong expectation
Black Screen
No notification
Proposal in English and without drop down value
SIT3: ADP_Demographic_Day2_01_Job Record_01-Field02_EMPLID: Field is not required for New hires as Payroll ID will not be captured initially. Need Requirement update.
able to choose a date in the past
INT032_Sailpoint_Phone Number mapping change
SIT3 - WFA_Day2_T0224_cust_Pay_Range_Max
Signing in permit
01-04-29 No Workflow Recieved on this Saved Transaction from (01-04-28)
Verify that user is able to create claims
MFT : Additional files are sent in MFT with incorrect format, as per chris meyer. Look more in Actual result section.
LTI_AZL_26-02_25_EC_OB_SendWordNow_Day2_T0025_PHONE 3 - record counts do not match between Outbound file and EC reporting
Strange Error Message when closing registration process (line manager registers employee)
AZLAD - The Phone number is formatted with a '.' per the new requirement change, there should not be any formatting. It is expected to be as area code + phone number
MFT : Actimize. No file present in Inbound Location
ServiceNow UI - Search is not working consistently in 'My position request' tab
Please enter correct E-Mail Adress for Notifications in the Line Manager and Instructor Profile
SIT TC: Feld 'Anfangsdatum der Kündigungsfrist' nicht im EC vorhanden
No forewarding to next page
INT033_SendWordNow_Calling_Tree_mapping change for the preferred name
Employee base to be preselected when requesting a date for a course (Terminanfrage)
INT030_FM_Interact_Phone Number mapping change
Massnahmen-Mapping bei Arbeitszeit für Replizierung in SAP nicht korrekt
ServiceNow UI - TASK0020276 represents POS0001098, when Tracy opens POS0001098, it shows fields for HR Services to fill whereas it is a replace position request and it should not have fields for HR Services.
Vorsatzwort 'aan' in Replikation gescheitert
ServiceNow - email notifications which include approve or decline links shall have a consistant format
LMS : Curricula Not Displayed
wrong event and event reason generated from reduction in hours (no permanent/temporary change)
LTI_AZL_ServiceNowUI : The field Canceled by (name of person who cancels form) is not present in the form
Unable to Edit Position as Line Manager for this test, however able to as HRS
No Line Manager?s name to click on
Orgchart - default value is showing some employee, without any hierarchy . default value is not the CEO screen.
SF LMS CR Translations
Cancelling the participation
HRS approval workflow notification not trigger for change disability
SIT3-AZL Orgchart: Inpatriate: One record didn't get in file: Neha Govind
Verify that functionlity A is working as expected.
Quality Resource Group(QRG) - inpatriate records are not pulled in the interface. (Note: sample records attached in actual result section)
Add SO: could not choose"equipment" and unclear what to do under "Custom Columns"
SIT2-EC-OB-Service Now-PositionDescription: Not full value is displayed for the Title from UI to file.
INT032_Sailpoint_mapping change for the preferred name
Testcase: Login as Linemanager instead of Employee
SIT2-EC-OB-PSoft Financial-Company Name: Allianz Global Corporate & Speciality AG is displayed which is not part of requirement for selection criteria.
Orgchart : source file(from EC) , phone number format is not correct for few records.
INT047_EC IB NetworkID Em Ph_Phone Number mapping change
ADP emp demographic rcipsoft
Amex Concur - There is no email change, from previous run and current run for a particular employee , but still it generated, "Record 320."
LMS : do not have add items and Curricula
SIT2-EC-OB-Service Now-DirectDialPhoneNumber-Not populated properly from UI to file and also not formatted as expected.
INT034_UPS_Trackpad_mapping change for the preferred name
Verify auto pass feature
SIT3- WFA_Day2_T0230_description
LTI_AZL_ServiceNowUI: There is no text/notification to indicate that a request has been cancelled successfully
Unable to add bank for employees & Test case incomplete
LMS: REPORT Error
Report "Item Requests" not visible.
The Position Cluster is just displaying a dash
No Email received for HRS for Personal data change by Employee
SIT2-EC-OB-Aztek-Suffix: Suffix is not enabled in UI and we are not getting any data in the field. Is this mapped correctly?
"View all" button is not visible in the SO-view
HRDB Interface - Date format issue
LM is not able to change direct report's employment details
SIT2-EC-OB-ADP Foundation-Completely missing Location record
No Email received for HRS for AddWorkEligibility case
OrgChart UI: Cost Centre : displaying init caps in orgchart UI, but in EC its all UPPER CASE. And only Cost Centre"name" is displayed . cost centre "number " not displayed.
Anlage einer Maßnahme in SAP ist falsch
Payroll:Item:Primary Bank Code
ServiceNowUI - Tracey is able to edit comp team fields,requestor fields,HR services fields and enter approval comments. It is expected that Tracey should be able to only assign recruiter.
Test scenario description - "Save instruction" is missing after altering settings in SO
HRDW_MAIN-EMPLOYEE: NATIONAL_ID_IS_PRIMARY displayed as ?0? for True and False.
Deep-Link Generator not available
Verify the system settings parameters
Unable to save the dependent record after editing as we received an error
SIT3 - WFA_Day2_T0233_effectiveStartDate
Error-Message after Starting the Admin-Center
OrgChart UI - Name: Not displaying correct values in org chart UI and the visio diagram. Existing CR already present for this,
HRDW_MAIN: IMPORT_WFA: Multiple fields need to be fixed for Boolean fields
SIT3: ADP Foundation: Tranformation rule is not working for Name Description field for 04 record.
SIT TC: Unsinniger Testfall - Keine Mitarbeiterkreispflege über Unternehmensinformation möglich
CoE-38cWithinDepartmentGrade13to15_Approval - Request for Geraldine Green Not in Pending Requests
LMS - users not added in record completion page
According to the test case, the LM should not have any permission.
Moved to a different cluster - No confirmation box/workflow triggered.
Modified eMail address is rejected during Feeder processing
ADP employee demo rcipsoft
SIT3-AZTek: Manager Name displayed is not accurate and not matching with UI.
SIT3 - WFA_Day2_T0090_leaveOfAbsenceStartDate
ID Number
ADP demographic rcipsoft ft to pt trans
LTI_AZL_06-02-04_EC_OB_QRG - Not every email address is showing up in Outbound files, but is populated in the EC UI
LMS - SIT - report screen not displayed
no Manager choice
Test Scenario description: step 28 - misleading/incorrect
LTI_AZL_14-01-114_EC_OB_HRReporting_WFA_Day1_T0114_initial-entry-date
AZL Integration - Apptio Integration CR - Header name change
APPTIO : Expatriates should be excluded in the interface file, as per the requirement. But they are present in the file. - File used. ECPth_Apptio_20170915113441
there is no field "My Employees"
Process to assign or remove courses to or from employees
HRBP-38bWithinDepartmentGrade13to15_Approval - Geraldine Green Pending Request Not Visible
SIT2-EC-OB-Aztek-Effective date is not displayed properly for the records.
ServiceNow UI - The fields which are mentioned as "Do not display in the SN form" could be removed from the requirement excel
Voluntary Term Reason defect - SIT3
LTI_AZL_14-01-40_EC_OB_HRReporting_WFA_Day1_T0040_bonusPayExpirationDate
SIT TC: Not able to maintain the field "Position Grade".
SIT2-EC-OB-Service Now- EmplID-Records missing even though they are valid records and not present in error report.
SAPe Recruiting - The SAPeRecruiting interface file is pulling the records to interface file based on the selection criteria + the required fields. No error report has been generated.
continue not possible
SIT Prep: Mailversand PZE aufgrund Geburt Kind
LTI_AZL_22-01-33_EC_OB_Success Factors OLC ATM - the field 'Title' picks the default value of positionTitle instead of positionTitle value.
ServiceNow UI - The Hiring Manager's Email is not being pulled through API call but is pulled form Service Now database. The requirement says that data for this field is pulled through API call.
LTI_AZL_01-02-06_EC_OB_SendWordNow - the outbound file should be Comma Delimited, but is coming as Pipe delimited
SIT3 - WFA_Day2_T0089_leaveOfAbsenceReturnDate
SIT3 - WFA_Day2_T0243_positionMatrixRelationship
ServiceNowUI - Not able to access the position request forms with HR services role
LMS: The option/button "Email when Complete" is not available in any of the available Reports.
EC_OB_ECPth_AZLAD - Email address is mandatory and it causes many records to be moved to error report
No email received for HRBP for rehire
ADP demo rcipsoft
Verify that user is able to generate claim reports
Unable to update Gender Field
AZLAD - The MobilePhone number is formatted with a '.' per the new requirement change, there should not be any formatting. It is expected to be as area code + phone number
ServiceNow UI - Bill G is able to see all types of position requests in the system, when clicked on 'My position requests' and when filter is removed
LMS : it only NA
INT013_SN_ServiceNow_mapping change for preferred name and header
Test description not correct, wrong log in information.
ServiceNow UI - Cancel comments window is not working as expected
SIT3 - WFA_Day2_T0282_variable_comp_external_code
Group requirements cannot be selected
LMS : no "Remove" button
Org chart ; Hierarchy from org chart not available in Visio diagram (only present partially)
Updates in HCM do not reach SF LMS
Event Reason Drop Down - NO Data & Unable to edit Compensation Info
ADP demographic file rcipsoft job code corr
Different search neccesssary
rcipsoft no salary related data in file
Position not showing up while adding a new employee
ServiceNow UI - While SLG member views the appovals task assigned "the date when the request was created" is being displayed instead of "the date when the request was submitted for approval"
Line Manageri is able to see employees address
Position cluster data not synchronized from Position in Employee File.
Einspielung in SAP
LTI_AZL_03_ServiceNow_T0023_Verification of Email - The initial Recruiter is not being CCed on the email to HR Mgr/Requestor at Recruiter Assigned state
01-04-49 HR Local-TransferWithinCountry
Warning Message
Nationality value not updated in My file
No confirmation, as registration was not possible, see step above
Able to see & update the Interim Grade Field
Missing Translation of "Learning Proposals"
Workflow is not Generating
016-AZ Active Directory - File name should begin with "ECArc" but its created with "EcArc"
LMS : Domain ID in SO is missing
SIT2-EC-OB-HR WFA-Date of Birth-Information is not populated in the file from UI.
LMS - Upon trying to open Item which was search - an error is popping up
LMS : do not have "Register Now"
SIT TC: Beschreibung stimmt nicht.
rcipsoft record types 4 and 5 effective dates
SIT3: HRDW_Report: Views are not loaded.
LTI_AZL_14-01-115_EC_OB_HRReporting_WFA_Day1_T0115_relationship-type
Amex Concur - Corporate Address- not displaying address from FO only for AMOSA Entiy. For all other enttiies its displaying correctly.
SIT3: AZTek: Record with valid manager name is missing in file and populated in error report, even though Manager Name is present.
FT2PT HRS initiating, no notification to LINE MANAGER (Salary grade 11)
LTI_AZL_11-02-02_EC_OB_Sailpoint : File has only one record in it. Unable to test. No error report was generated.
Incorrect Test Case Scenario: >grade 16
System notification for Disability status change
0% Leading position should not be terminated
Verify the cheque credit process is as expected
No "Zusatzwort" available
No Commerce Tab Available, Please check Role of User
Verify the reports generated in dashboard
rcipsoft file home department
Manager Termination - did not move specific Position to new LM - is this expected behavior?
The field "Function" is supposed to appear, however the field "Vorname" is shown
Verify that functionlity Q is working as expected.
Verify functions data is add
Closed: Overwriting Title with the Job Type
Cannot be done, as "register now" cannot be found
No authorized classes available
There is no translation on the left side of the page
INT026_Org_Chart_Phone number mapping change
System loads forever
Verify disclaimer section is correct
SIT2-EC-OB-SAP eRecruiting-Employee1-Network ID: If the user is missing network ID, record is not populated in the file.
ADP demo file rcipsoft
Not possilble, cause i should specify an "end-status" (=Abschlußstatus")
INT025_Apptio_IT_Financial_Portfolio_mapping change for preferred name