## Sheet1
0
0 | Translation of Survey
1 | HRS does not have direct reports to change pay targets
2 | Item cannot be found - test case/description should be changed.
3 | FM Interact - Required fields are mapped but defaulted to null. Since its marked mandatory, records are not pulled by interface.
4 | LTI_AZL_14-01-115_EC_OB_HRReporting_WFA_Day1_T0115_relationship-type
5 | rcipsoft file home department
6 | INT030_FM_Interact_Phone Number mapping change
7 | MFT: Onbase - No file in MFT Inbound/Archive location for 15sep
8 | Keine Übersetzung für "External Training Request" + "Learning Proposal" (unter Startseite-Schulung -> Verknüpfungen) sowie die Seiten dahinter!
9 | System loads forever
10 | Test scenario description - "Save instruction" is missing after altering settings in SO
11 | Keine Schaltflächen zum Schliessen des Fensters
12 | LMS : Learning proposal link missing
13 | SIT2-EC-OB-Actimize-Day1: New hire entered on 7/12 is not included in the file generated.
14 | SIT3 - WFA_Day2_T0222_cust_Pay_range_Currency
15 | approval needed
16 | LTI_AZL_22-02-37_EC_OB_Success Factors OLC ATM - Field 'Full or Part Time' is BLANK when employee-class = Inpatriate
17 | Unable to update status after outbound-webservice
18 | Retest
19 | SIT2-EC_OB_HRReporting_WFA_Day1_T0064_country-of-company: Data not populated in file from UI
20 | Incorrect Test Case Scenario: >grade 16
21 | After data update through feeder cost center is not transferred
22 | In record type type the User 2 Char field is limited to 30 rcipsoft
23 | Create New Defect_DEMO
24 | LMS - SIT
25 | Different field names in hiring action and position object
26 | SIT2-EC-OB-GIAM ID-Identity Status- Terminated records will not be in file and we cannot test the value with "2".
27 | LMS - users not added in record completion page
28 | Manager is able to see scorecard
29 | LTI_AZL_26-02_18_EC_OB_SendWordNow_Day2_T0018_CUSTOM VALUE 4 - Data issue
30 | SIT_1_EC: Fehlerhafte Anzeige der Kachel DEÜV
31 | INT 016 AZ SE Active Directory- CompanyName transformation value not working as per the rule. When Employing entity = 'Allianz Life Insurance Company' set to 'Allianz Life Insurance Company of N'
32 | SIT2-EC-OB-Service Now-Header Record is missing from the file.
33 | SIT2-EC-OB-GIAM ID-DataSupplierNo field cannot be validated as its not displayed in UI and default values are displayed.
34 | 01-14-01 HRS-OETransfer
35 | Classification not available
36 | Payroll:Item:Web User Name
37 | Gender field not visible in MSS
38 | SIT3-GIAM SE ID_Day2_T0022_ID-TempDeactivationStartDate: Effective date is not reflected in the file for this field
39 | SIT2-EC-OB-SFOLCATM-Status: Included Terminations from more than past 10 days from run date.
40 | SIT3 - WFA_Day2_T0243_positionMatrixRelationship
41 | Disbility field available for LM
42 | SIT3 - WFA_Day2_T0277_position_loc_state
43 | Amex Concur - There is no email change, from previous run and current run for a particular employee , but still it generated, "Record 320."
44 | SIT TC: Missing Step in Testcase
45 | Orgchart - default value is showing some employee, without any hierarchy . default value is not the CEO screen.
46 | Signing in permit
47 | LTI_AZL_11-02-02_EC_OB_Sailpoint : File has only one record in it. Unable to test. No error report was generated.
48 | SIT2-EC-OB-GIAM ID-PostalZIPCode not populated from Entity level but populated from Employee level.
49 | SIT2-EC-OB-Service Now- EmplID-Records missing even though they are valid records and not present in error report.
50 | Manager can see position orgchart
51 | No forewarding to next page
52 | National ID email trigger- change in subject line
53 | ServiceNow_UAT_Enhancements - Error message displayed is 'Manager not found and Error - Position not found' where as the user did not yet attempt to fill the Manager's name
54 | SAP JAM window not closeable
55 | Test to conduct on various merchants
56 | SIT2-EC-OB-SAP eRecruiting-Positions: Some positions are not displayed in file
57 | INT042_GIAM_Phone Number mapping change
58 | Non-Employee Referral functionality - questions
59 | SIT TC: Bezeichnung im DropDown-Menü anders als in der Description
60 | SIT Prep: Fehlende Umlaute in Bezeichnungen und Adresse
61 | LOA Start & end date not visible under Job information of employee
62 | INT013_SN_ServiceNow_mapping change for preferred name and header
63 | HRDB Interface - Date format issue
64 | LMS : Option 'Learning' not visible under 'Home'
65 | Amex Concur - Record 310_Active field -For 3 records, N is populated , instead of default value Y
66 | LMS : Employee can see admin centre
67 | Manage Link Missing for HRBP
68 | Deep-Link Generator not available
69 | 0% Leading position should not be terminated
70 | Fehlerhafte Abgrenzung der SAP-Infotypen 0000 und 0001
71 | ADP emmployee data rcipsoft dup record
72 | CONVERSION Instance: HRDW_MAIN.POSITION_DETAIL: HR WFA: Corporate State is not displayed in 2 fields in HR WFA file
73 | The Bank ID field is not auto populated.
74 | ServiceNow UI - When a position request is in the status 'Pending Approval' Tracy is still able to edit the form and assign recruiter.
75 | There is no translation on the left side of the page
76 | Einspielung in SAP
77 | AZLAD - For one of the header field, the FS has 'Jobcode' but the interface file has 'Jobcode Desc'. The field is actually mapped to externalname (Position). Please clarify if it should be 'Jobcode' or 'Jobcode Desc'
78 | SIT TC: Testfall nicht klar
79 | Address Change - The field "District" is not available.
80 | Search not working due to user account fault
81 | Conversion File-HR WFA-Position field is coming as blank for 24 records.
82 | SIT TC: Not able to maintain the field "Position Grade".
83 | Cancelled LOA is not shown in History of Job information
84 | SIT Prep: Keine GDT-Zuordnung für PERSONNEL_EVENT_TYPE_CODEs
85 | INT016-AZSE Active Directory - PersonaIid field mapped to custom-string9 and field is marked as"Required".the interface need to includes non-employees who might not have payroll id
86 | HRS not able to change history of Job Info
87 | SIT3-Servicenow-Emplstatus- Coming as "A" even for Dormant status. when employee is on Global Assignment at presnt.
88 | Verify auto pass feature
89 | Test to verify user authentication
90 | LTI_AZL_22-02-03_EC_OB_Success Factors OLC ATM - Header 1 is missing in the file
91 | Holding Division Appears under the "Manage Data" section in the Admin Center not the "Manage Organisation, Pay and Job Structures"
92 | DropDown "Bevorzugter Standort" ist leer
93 | No email received for HRBP for rehire
94 | INT008_Rivermine_mapping change for preferred name
95 | LTI_AZL_ServiceNowUI_Discrepencies with the finance consultants name
96 | LMS: Approval Step Missing
97 | NPS Scale shows "6" twice instead of "8"
98 | SIT3 - WFA_Day2_T0251_name
99 | SIT1 : Infterface - Field {First Pay Date} Career file
100 | LTI_AZL_ServiceNowUI : When the user is navigated to second page of the request form, a text is being displayed that position request is submitted wheras the request is not yet submitted
101 | Please enter correct E-Mail Adress for Notifications in the Line Manager and Instructor Profile
102 | SIT2-EC_OB_HRReporting_WFA_Day1_T0213_externalCode: data not populated as expected in file from UI
103 | No email notification
104 | can't select course
105 | Field not shown
106 | Payroll:Item:Gender
107 | 01-04-44 Incorrect Event/Event Reason on Transaction, No Popup Window, No Workflow
108 | Verify the reports generated in dashboard
109 | NUll pointer Exception
110 | SIT2-EC_OB_QRG_Day1_T0010_MAIL_CITY: Data is not coming from Corporate City field
111 | LMS : there is no available course date
112 | AZIND004_HRDB_EE - Manager ECID
113 | Massnahmen-Mapping bei Arbeitszeit für Replizierung in SAP nicht korrekt
114 | Begrenzung bestehender Datensätze in SAP
115 | Proposal in English and without drop down value
116 | SIT2-EC_OB_HRReporting_WFA_Day1_T0214_name: Data is not populated from Ui to File
117 | Revison date and time cannot be entered; no hints to formate
118 | Unable to add a new Holding Division as admin "rakins"
119 | INT034_UPS_Trackpad_mapping change for the preferred name
120 | LM cannot able to terminate an employee
121 | SIT2-EC-OB-Service Now-DirectDialPhoneNumber-Not populated properly from UI to file and also not formatted as expected.
122 | LTI_AZL_ServiceNowUI - Finance consultants names are not available in the UI
123 | rcipsoft keeps processing
124 | Gerhaltsinfo bei Neueintritt
125 | ServiceNow UI - Under the HR panel in the left there is a tab 'Position Request SLG Requests' which is the same for all the approvers/team. Probably it could be renamed to be generic.
126 | Email List Automation - The file is expected to have just 28 email addresses of supervisors but in actual the file is pulling 213 records with non supervisor email addresses as well
127 | When keying a term the option of what to do with direct reports is different
128 | various languages(English, German, French) appear on the website under "My Employee File"
129 | ServiceNow UI - Cancel comments field is editable for HRBP, only requestor should be able to cancel a request and will be prompted to enter cancel comments.
130 | Test different methods of routing
131 | able to choose a date in the past
132 | COE didnt receive approval mail for promotion 16 and above
133 | Fehler bei Eingabe einer Bank im Ausland
134 | SIT3: ADP_Demographic_Day2_01_Job Record_01-Field02_EMPLID: Field is not required for New hires as Payroll ID will not be captured initially. Need Requirement update.
135 | Edit or Manage Position error
136 | Summary Defect for HR factory role permissions
137 | SendWordNow : PHONE 3 field not populated with phone number. instead its populated with 1
138 | INT026_Org_Chart_Phone number mapping change
139 | Line Manager sagt Maßnahme für MA ab: unverständlicher 2. Warnhinweis
140 | LTI_AZL_26-02_20_EC_OB_SendWordNow_Day2_T0023_PHONE 2 - Outbound file record count does not match with EC report for same business rule
141 | DVFS: Last date worked is being pulled for certain records which are not terminated.
142 | Sailpoint : Employee type field is populating "N"
143 | Different search neccesssary
144 | Email List Automation - There is no data in the HRADM.EMAIL_DIST_LIST_EXCEPTIONS table.
145 | close position is working.. but there is no difference between close position & freeze position
146 | ServiceNow - email notifications which include approve or decline links shall have a consistant format
147 | ServiceNow UI - The Hiring Manager's Email is not being pulled through API call but is pulled form Service Now database. The requirement says that data for this field is pulled through API call.
148 | Verify that functionlity Q is working as expected.
149 | SIT_1 EC: Fehlerhafte Anzeige der Kacheln
150 | Email List Automation - The record Test2357@allianz.com is expected to be in the file. This is being fetched when the QA query is run, but we do not find it in the generated file.
151 | Kursleiter
152 | Newly created record not pulled in the extract file- CybershiftUserprofile though matching the criteria.
153 | HRDW_Main: Position: POSITION_FTE: Displayed round off numbers instead of 2 decimals.-
154 | SIT2-EC-OB-Aztek-Effective date is not displayed properly for the records.
155 | HRDW_MAIN: Position: Vacant: Displayed ?0? for True and False values
156 | 016-AZ Active Directory - File name should begin with "ECArc" but its created with "EcArc"
157 | Verify that bonus payout feature is correct
158 | test
159 | Link does not work
160 | LTI_AZL_03_ServiceNow_T0004_UserInterface - User is seeing more PRs than their own
161 | SIT3: AZTek: Record with valid manager name is missing in file and populated in error report, even though Manager Name is present.
162 | Unable to save the new employee as it is asking to provide the bank number which is not a mandatory field
163 | LTI_AZL_03_ServiceNow_T0003_UserInterface - Hover over text is missing for required fields
164 | LM can see the employees bank details
165 | HRS-63AddSalesCompensationPlanNon-EmployeeReferral
166 | LTI_AZL_ServiceNowUI: The field 'Cancel Comments' is not present. The user is not prompted to enter any comments when the request is being cancelled.
167 | Nationality value not updated in My file
168 | LOA Issue
169 | Unable to Edit Position as Line Manager for this test, however able to as HRS
170 | SIT2-EC_OB_HRReporting_WFA_Day1_T0028_primary_flag: Emergency Primary flag is not populated
171 | Email List Automation - Unable to access the generated files. It says 'Access denied'
172 | HRDW_MAIN: IMPORT_WFA: Multiple fields need to be fixed for Boolean fields
173 | SIT TC: No field "notice period"
174 | Error Message poped up after clicking on search
175 | EC_OB_Day1-AZTek-Phone Prefix Number: Area code from phone number is not loaded to this field.
176 | Email List Automation - As per the query in the mapping document it is expected to fetch 0 records in the file but I could see 85 records in the file.
177 | Test Scenario description: step 28 - misleading/incorrect
178 | Cancelling the participation
179 | LMS : do not have "Register Now"
180 | SIT2-EC_OB_HRReporting_WFA_Day1_T0258_defaultPayGroup: Data is not populated from UI to File
181 | ECPth_Apptio_CCYYMMDDHHMMSS.csv - Mgrclock transformation not working as expected
182 | LTI_AZL_14-01-40_EC_OB_HRReporting_WFA_Day1_T0040_bonusPayExpirationDate
183 | ServiceNow UI - Bill G is able to see all types of position requests in the system, when clicked on 'My position requests' and when filter is removed
184 | ServiceNow UI - Tracy is able to view one draft request under 'Position request my tasks'.
185 | LTI_AZL_03_ServiceNow_T0013_Verification of Email - ServiceNow - text in email is different from requirements
186 | SIT3 - WFA_Day2_T0282_variable_comp_external_code
187 | SIT3-ServiceNow-MobilePhone: Getting Business Mobile number instead of Home Mobile.
188 | Email List Automation - There is one duplicate record in the file EOKeyInfluence1 file
189 | Payroll:Item:Category Code
190 | ADP emp demographic rcipsoft
191 | LM did not receive probation period alert notification
192 | LM - RBP - Position Mgmt - Position Grade & Job Code are visible to the LM.
193 | LTI_AZL_22-01-31_EC_OB_Success Factors OLC ATM - translation rule for 'Employee type' is not mentioned in FS for terminated employees.
194 | SIT3 - WFA_Day2_T0224_cust_Pay_Range_Max
195 | LMS : No Option of "Return to Curriculum" is displayed
196 | SIT2-EC-OB-SFOLCATM-Selection Criteria-Non-employees are not populated as Local ID will be missing. Update to requirement needed
197 | AZLAD - Inpat records are NEITHER present in the interface file NOR in the error report.
198 | ServiceNow UI - When a modify position request is in 'Draft' status the comp team member is able to view and edit the entire form.
199 | Title "Bankverbindungen" not available
200 | HRDW_MAIN.Emergency_Contact: Displays "0" instead of True
201 | ServiceNow UI - TASK0020276 represents POS0001098, when Tracy opens POS0001098, it shows fields for HR Services to fill whereas it is a replace position request and it should not have fields for HR Services.
202 | SIT3-INT013 Service Now: Update extract logic for existing EMPLID field to populate the PSoft Legacy ID (Biographical Information.custom-string8).
203 | LM not receiving workflow notification on Job Change (PT to FT, FT to PT)
204 | HRBP not able to view Position Grade or Job Code
205 | Cannot Save without "Classification"
206 | SIT3 - WFA_Day2_T0223_cust_Pay_range_Frequency
207 | SIT2-EC-OB-Service Now-PositionDescription: Not full value is displayed for the Title from UI to file.
208 | ServiceNow UI - Unable to fetch position request details using SAOP UI. Eorror message is being displayed.
209 | ServiceNow application does not allow the HR Comp person to use "Permanent" as a valid Employee Status - hangs the system
210 | INT016_AZ_SE_Active_Directory_mapping change for preferred name and header
211 | Edit position option is not availabe for HRBP
212 | ServiceNow UI - Tracy is able to assign recruiter but the status of the form is not being moved to 'Recruiter Assigned' even after close completing the task.
213 | Can not register any test-user
214 | INT033_SendWordNow_Calling_Tree_mapping change for the preferred name
215 | ServiceNow - Cancel notification email is not formatted according to the requirements
216 | Unable to see add option in personal information for creating ethnicity
217 | The Recurring Absence Check Box is Greyed Out - Script needs to be updated.
218 | Rivermine Enriched file: FinancialApprover logic not correct, Doug/Tony to confirm the join condition to be used to derive the logic.
219 | Unable to add bank for employees & Test case incomplete
220 | Unable to save the dependent record after editing as we received an error
221 | LTI_AZL_22-01-12_EC_OB_Success Factors OLC ATM - Manager USERID is fetching NO_MANAGER when there is no manager listed eventhough the condition is not stated in FS
222 | Verify existing user re registration
223 | Missing Picklist for "Quelle"/ Source
224 | Required permissions are missing to edit "Locations"
225 | Org Chart - made updates to fields to be optional
226 | SIT3 - Psoft Financial_Day2_T0013_terminationdate
227 | No Commerce Tab Available, Please check Role of User
228 | LTI_AZL_22-01-32_EC_OB_Success Factors OLC ATM - For many records Manager Category <> People Manager but still ithe field 'people manager; populating as 'yes'
229 | Report "Item Requests" not visible.
230 | Payroll: NewJoiner
231 | ID Number
232 | Verify that new shipment is created
233 | there is no field "My Employees"
234 | MFT : Actimize. No file present in Inbound Location
235 | LTI_AZL_11-02-12_EC_OB_Sailpoint_Job Title is picking data from Job Title instead of name(Position FO)
236 | SIT3-AZL Orgchart: Inpatriate: One record didn't get in file: Neha Govind
237 | ServiceNow UI - API calls - The API call is expected to pull the HRBP Position ID (matrix relationship) but in actual it populates the original position ID itself.
238 | LMS : no remove page
239 | 016-016-AZ SE Active Directory - BusnPhone , not including the area_code.Clarify if its business mobile / business landline .
240 | ServiceNow UI - There are two 'My self service' menu in the homepage for Melania Meyer only
241 | LTI_AZL_01-02-06_EC_OB_Actimize - 1 employee has a Salutation of a number in EC, but "Dr." as Salutation in outbound file
242 | Line Manageri is able to see employees address
243 | Process to assign or remove courses to or from employees
244 | Test Scenario description: Missing steps?
245 | Change of date when copying a position
246 | ServiceNowUI - Not able to access the position request forms with HR services role
247 | Not only "Admin Center" in dropdown
248 | LTI_AZL_06-02-06_EC_OB_UPS Trackpad_Day2_T0006_CostCenter - Cost Center data in Outbound file is not matching with Cost Center data in EC
249 | Search not possible - without hits
250 | FT2PT HRS initiating, no notification to LINE MANAGER (Salary grade 11)
251 | SIT2-EC-OB-Aztek-Suffix: Suffix is not enabled in UI and we are not getting any data in the field. Is this mapped correctly?
252 | LTI_AZL_22-01-20_EC_OB_Success Factors OLC ATM_Day1 - EMPLID is directly mapped to Local ID with no translation rule.
253 | HRBP didnt receive notification on Assigning LOA Paid & Unpaid
254 | Not all fields are copied with "add peer position"
255 | EC Config
256 | Create Online Item - Drop down "item type" (DE: Elementtyp) does not offer "ONLINE COURSE"
257 | Test description not correct, wrong log in information.
258 | Worksheets aren#t launched for Amina Lateef
259 | Unable to update Gender Field
260 | LMS - SIT - report screen not displayed
261 | ServiceNow UI - The field should '% increase' allow ony 2 decimal places but it allowes more than two
262 | All mandatory fields are filled, but error message raises
263 | Wording of "Warnhinweis" to be modified to "Hinweis"
264 | Error-Message after Starting the Admin-Center
265 | Verify response time is as expected
266 | SIT2-EC-OB-SAP eRecruiting-Employee1-Network ID: If the user is missing network ID, record is not populated in the file.
267 | SIT TC: Grade not editable
268 | HRDW---PRE_PS_DATA need to be loaded in HRDWTST1
269 | Cannot be done, as "register now" cannot be found
270 | ADP employee demo rcipsoft
271 | ServiceNow UI - Unable to look up requests as hiring manager and cancel the same.
272 | LTI_AZL_26-02_25_EC_OB_SendWordNow_Day2_T0025_PHONE 3 - record counts do not match between Outbound file and EC reporting
273 | AZLAD - The Phone number is formatted with a '.' per the new requirement change, there should not be any formatting. It is expected to be as area code + phone number
274 | LTI_AZL_ServiceNowUI : The field Canceled by (name of person who cancels form) is not present in the form
275 | AZLAD - The MobilePhone number is formatted with a '.' per the new requirement change, there should not be any formatting. It is expected to be as area code + phone number
276 | INT032_Sailpoint_Phone Number mapping change
277 | Translation of Complete Page
278 | LMS : Domain ID in SO is missing
279 | Verify auto upgradation feature
280 | LMS : do not have add items and Curricula
281 | Some reports not found
282 | 01-04-49 HR Local-TransferWithinCountry
283 | FM Interact:: Incorrect Error Report : Employees have hiredate, but the records errored out with message "Error in the field [Current_Hire_Date] for the Employee:"
284 | Verify legal policy module changes
285 | No Line Manager?s name to click on
286 | MFT : HR WFA -No file in MFT Inbound location for 13, 14th and 15sep
287 | Search Bar Defect
288 | Target LM did not receive Notification
289 | LMS : no "Remove" button
290 | ServiceNowUI_A comp team member should be able to edit only a few API fields in the requestor form, currently the entire form is editable for a comp team member.
291 | SIT3 - WFA_Day2_T0225_cust_Pay_Range_Mid
292 | Employee did not receive notification for Work Eligibility
293 | SIT3- WFA_Day2_T0230_description
294 | Anlage SAP Infotyp 0000 darf nicht erfolgen
295 | No "Zusatzwort" available
296 | Translation Defects/ Sammeldefekt
297 | Step 13 cannot be fulfilled, as there are no registrations
298 | SIT: AZLife Orgchart_Day2_T0006_EmployeeFirstName: Preferred name is moved instead of First Name
299 | INT010_VolunteerMatch_mapping change for preferred name
300 | SIT2-EC-OB-PSoft Financial-Company Name: Allianz Global Corporate & Speciality AG is displayed which is not part of requirement for selection criteria.
301 | ServiceNow UI - An extra field 'Send for Approval' is present in the requestor form while I create a position request.
302 | Tab for Position Org Chart exists if User is Manager
303 | HRBP-33cManageLayOffs_Approval
304 | Language Mixture after switching the language from EN to DE
305 | CR : If Employee Class = Contractor, Interface should not pick up the employee
306 | Success Factors OLC ATM - Duplicate record found
307 | Able to see & update the Interim Grade Field
308 | Interim Grade Field - Not editable by HRBP
309 | SIT2-EC-OB-SAP eRecruiting-Org units file-Business Unit/Board unit that has Amosa as Employee Entity is displayed in Org Units file 1.
310 | LTI_AZL_26-02_21_EC_OB_SendWordNow_Day2_T0021_PHONE 1 - Outbound file record count and report from EC record count does not match
311 | Unabe to select SGP position in LM field while creating position
312 | MFT: No file present for " ADP - Employee Demographics" in ADP Inbound folder. Latest file present was for11th sep
313 | SIT2-EC-OB-ADP Foundation-Completely missing Location record
314 | No message displayed for dependent birth certificate, instead data saved successfully occured.
315 | Position Cluster displaying a Dash
316 | HRDB_EE-Role missing
317 | No Email received for HRS for AddWorkEligibility case
318 | Commerce icon is not showed
319 | Position cluster data not synchronized from Position in Employee File.
320 | HRDW_MAIN.Emergency_Contact: Records displayed in the table even when no emergency contact detail information exists.
321 | ServiceNow UI - While SLG member views the appovals task assigned "the date when the request was created" is being displayed instead of "the date when the request was submitted for approval"
322 | SIT TC: Beschreibung stimmt nicht.
323 | LTI_AZL_14-01-114_EC_OB_HRReporting_WFA_Day1_T0114_initial-entry-date
324 | ADP demo rcipsoft
325 | Change of Compensation Info is possible for LM
326 | There are no courses available
327 | No notification
328 | INT016 - AZSEAD - File generated with only one record.EcArc_AZSEAD_20170912113617
329 | rcipsoft record types 4 and 5 effective dates
330 | Payroll:Item:Occupation Code
331 | Add SO: could not choose"equipment" and unclear what to do under "Custom Columns"
332 | LTI_AZL_03_ServiceNow_T0023_Verification of Email - The initial Recruiter is not being CCed on the email to HR Mgr/Requestor at Recruiter Assigned state
333 | Success Factors OLC ATM - The file isn't pulling retro records (terminated > 10 days before but updated in EC < 10 days in the past)
334 | Genehmigung durch HRS erforderlich bei Angabe Auslandsüberweisung und Bank aus Deutschland
335 | Can't login
336 | Verify disclaimer section is correct
337 | LTI_AZL_26-02_27_EC_OB_SendWordNow_Day2_T0027_SMS 1 - Outbound file and EC report record counts don't seem to match using the same Business Rule and Entities
338 | SIT3: ADP Foundation: Tranformation rule is not working for Name Description field for 04 record.
339 | LTI_AZL_03_ServiceNow_T0044_Verification of Email - in HRBP email notification, the body of the email begins with the word "Body"
340 | volunteermatch: default location setup missing for 8 entities
341 | LTI_AZL_03_ServiceNow_T0032_Verification of Email - ServiceNow - The email notification to the first Approver has wrong Email Header
342 | HRDW: Global Assignment table displayed 4214 record moved to table even though we don't have data for the global assignment columns
343 | No Add button for Delegation
344 | SAPeRecruiting - The Employee file 2 is not pulling any records for Emp Class = Intern / Working Student / Trainee.
345 | Verify that API response for M1 is correct
346 | EC_OB_ECPth_AZLAD - ipPhone is not populating area code
347 | Manager Termination - did not move specific Position to new LM - is this expected behavior?
348 | Verify that functionlity P is working as expected.
349 | SIT3 - WFA_Day2_T0283_variable_comp_external_name
350 | no recommendation available
351 | Black screen. Errrormessage
352 | HRS-63A:
353 | Enriched Cybershift Userprofie : EmployeeEndDate - showing incorrect value. 22025-12-31 instead of 2025-12-31
354 | LTI_AZL_29-02-01_EC_OB_UPS Trackpad_Employee Class - Some EEs appear to be missing from the Outbound file that DO appear in EC and follow the Business Rules
355 | ServiceNow UI - Cancel comments window is not working as expected
356 | Enriched_ServiceNow - There is no value mentioned in the FS under Field Label (Used for Header Record) for Employee ID
357 | The field "Function" is supposed to appear, however the field "Vorname" is shown
358 | LMS : The said field is not visible
359 | HRDW_MAIN-EMPLOYEE: NATIONAL_ID_IS_PRIMARY displayed as ?0? for True and False.
360 | SIT2-EC-OB-SAP eRecruiting Employee1-Birthdate is missing from the file even though records have data in UI.
361 | LMS - No option to withdraw from course
362 | SIT3: HRDW_Report: Views are not loaded.
363 | Employee can view Purpose field under bank info
364 | SIT3 - WFA_Day2_T0233_effectiveStartDate
365 | "Questionnare Survey" not visible
366 | Not possilble, cause i should specify an "end-status" (=Abschlußstatus")
367 | Org chart dewtails missing in the file
368 | ADP demographic file rcipsoft job code corr
369 | Barzahler konnte ausgewählt werden
370 | Modifications to Names are not Showing up in the EC Search by Name List
371 | SIT2-EC-OB-HR WFA-Date of Birth-Information is not populated in the file from UI.
372 | SIT3 - WFA_Day2_T0248_vacant
373 | LTI_AZL_03_ServiceNow_T0036_Verification of Email - Email to Hiring Manager & Requestor has "New" in the subject and in the Body but should not
374 | Warnhinweis ausgewähltes Element ist bereits mit einer anderen Umfrage verknüpft, es ist aber keine andere Umfrage verknüpft
375 | SIT2-EC-OB-HR WFA-Email Address(B)-Not displaying the correct email address for the record.
376 | continue not possible
377 | ServiceNow UI - Picklist to be removed from the approval task
378 | Missing Translation of "Learning Proposals"
379 | Closed: Overwriting Title with the Job Type
380 | SIT TC
381 | Meldung erscheint nicht.
382 | Org chart ; Hierarchy from org chart not available in Visio diagram (only present partially)
383 | Payroll:Item:Primary Bank Code
384 | LMS : it only NA
385 | step useless
386 | Position Management - Position ID
387 | LTI_AZL_ServiceNowUI_Day1_T0100_Verify that the appropriate roles are able to provide proxy approval - Recruiter does not have permission to complete Approval Tasks on behalf of Approvers
388 | LMS - Scheduled classes issue
389 | HRDW_MAIN.JOB_INFO: IS_FULLTIME_EMPLOYEE displaying "0" for True and False.
390 | SIT Prep: Mailversand PZE aufgrund Geburt Kind
391 | After the LOA submission, details of the employee status is wrong in Job information
392 | Mistake in Test Process - wrong expectation
393 | LTI_AZL_ServiceNowUI_Day1_T0069_Verify that the appropriate roles are able to decline modify position requests - HRBP is unable to decline a Employee Change in Position PR
394 | SAP eRecruit - As per the FS the field 'BIRTHDATE' should not pull any values, it should populate only 'null' values. But the interface file has birthdates pulled from the UI.
395 | Orgchart UI: when scrolling down the viso diagram, the search button displays over the org chart visio diagram
396 | LTI_AZL_11-02-14_EC_OB_Sailpoint_Business unit name mapping issues
397 | Closed: CR 41-2018 Übersetzung Adresstypen
398 | no fields tu fill in
399 | LTI_AZL_ServiceNowUI: No notification/text is being displayed when a position request is submitted
400 | MFT : FM Interact. Additional 4 files are present in the location generated on 9/13, other than expected file and 1 file dated 9/14. File name :Employee_20170914045650.csv.pgp &_20170~2. Refer attachment for more details
401 | LTI_AZL_ServiceNowUI: Update button is not working as expected
402 | No Email received for HRS for Personal data change by Employee
403 | LTI_AZL_ServiceNowUI: There is no text/notification to indicate that a request has been cancelled successfully
404 | INT047_EC IB NetworkID Em Ph_Phone Number mapping change
405 | Es öffnet sich kein Popup-Fenster. Man kommt gleich zurück zu "Persönliche Informationen".
406 | Orgchart : source file(from EC) , phone number format is not correct for few records.
407 | SIT3 - WFA_Day2_T0089_leaveOfAbsenceReturnDate
408 | Org chart - Get visio diagram(hierarchy) not working from Google chrome. If any IE screens are open, then it opens the visio . else doesnot open.
409 | Verify functions data is add
410 | 01-13-16 HRS-JobChangeLateralMove
411 | No authorized classes available
412 | Change Main Bank IBAN
413 | ServiceNow UI - Search is not working consistently in 'My position request' tab
414 | HRDW_MAIN.Employment_Info: ELIGIBLE_FOR_STOCK coming as "0" instead of Trure/False(0/1)
415 | Verify that user is able to generate claim reports
416 | Verify that functionlity A is working as expected.
417 | Felder "Dependents"
418 | HRS-38aWithinDepartmentGrade13to15 - Did Not Interpret As Lateral but Data Change
419 | INT025_Apptio_IT_Financial_Portfolio_mapping change for preferred name
420 | HRBP-38bWithinDepartmentGrade13to15_Approval - Geraldine Green Pending Request Not Visible
421 | OrgChart UI: Cost Centre : displaying init caps in orgchart UI, but in EC its all UPPER CASE. And only Cost Centre"name" is displayed . cost centre "number " not displayed.
422 | No confirmation, as registration was not possible, see step above
423 | Position not showing up while adding a new employee
424 | SIT2-EC_OB_HRReporting_WFA_Day1_T0105_timeInPosition: Data in this field is not coming for all records
425 | Not able to save bank info
426 | Enriched_ServiceNow - There is no value for cube location in the enriched file. The column is entirely blank.
427 | SIT3-AZtek-Job Title from Fo Position Title, even though its present record is populated in error report as missing title.
428 | ADP demographic rcipsoft ft to pt trans
429 | Only 3 instead of 4 Tabs displayed
430 | LTI_AZL_26-02_26_EC_OB_SendWordNow_Day2_T0026_EMAIL 1 - Outbound file and report out of EC do not match for Email 1 field when using the same business rule
431 | Unable to view position as the HRBP in the Position Org Chart
432 | Popup-Fenster erscheint nicht
433 | MFT : Enriched file: Org Chart- File not present for 14th adn 15th
434 | Voluntary Term Reason defect - SIT3
435 | According to the test case, the LM should not have any permission.
436 | LTI_AZL_22-01-33_EC_OB_Success Factors OLC ATM - the field 'Title' picks the default value of positionTitle instead of positionTitle value.
437 | SIT2-EC-OB-ADP-EMPLID-Not displayed for all the records even though its required
438 | Employee did not receive notification for personal data change
439 | no ending pipe in record type 3 rcipsoft
440 | SIt2-EC_OB_HRReporting_WFA_Day1_T0104_timeInJob: Data not displayed for this field in file for all records.
441 | LTI_AZL_06-02-04_EC_OB_QRG - Not every email address is showing up in Outbound files, but is populated in the EC UI
442 | Verify landlord insurance policy and be modified
443 | SIT2-EC_OB_HRReporting_WFA_Day1_Impat Scenario is not coming in the file
444 | LMS - Upon trying to open Item which was search - an error is popping up
445 | Strange Error Message when closing registration process (line manager registers employee)
446 | Delivered Corrupted file- ECPth_CybershiftElement_20170714121916. Unable to open the file in excel/notepad/ultraedit
447 | Success Factors OLC ATM - The file isn't pulling any retired records.
448 | SAP eRecruit - One Inpat record which meets all the selection criteria is not showing up in the interface file.
449 | LTI_AZL_01-02-06_EC_OB_SendWordNow - the outbound file should be Comma Delimited, but is coming as Pipe delimited
450 | Moved to a different cluster - No confirmation box/workflow triggered.
451 | Payroll:Item:Marital Status
452 | LTI_AZL_29-02-01_EC_OB_Quality Resource Group_Employee Class - QRG - Not all INTERNS are coming into the Outbound file
453 | Org Chart UI- Fields Company, Division,Department, Cost Center, Line Manager, Position Title - cases should be maintained as is in file
454 | HRS able to change their own position and manager
455 | Enriched : Cybershift Userprofile - field "EmployeeLevel (col 1084-1133)" - truncated the first char of the string. Instead of Mgmt , its shows "gmt"
456 | LMS : Curricula Not Displayed
457 | Vorsatzwort 'aan' in Replikation gescheitert
458 | Can't choose "My employees"
459 | ServiceNowUI - Tracey is able to edit comp team fields,requestor fields,HR services fields and enter approval comments. It is expected that Tracey should be able to only assign recruiter.
460 | SIT2-EC-OB-PSOFT: Data chage record populated for one scenarios but not for other.
461 | SIT3-AZTek: Manager Name displayed is not accurate and not matching with UI.
462 | Warnhinweis ein ausgewähltes Element ist bereits mit einer anderen Umfrage verknüpft, dies ist allerdings nicht korrekt
463 | Payroll:Item:P.F. Registration Code
464 | SIT TC: Feld 'Anfangsdatum der Kündigungsfrist' nicht im EC vorhanden
465 | wrong event and event reason generated from reduction in hours (no permanent/temporary change)
466 | "View all" button is not visible in the SO-view
467 | Black Screen
468 | Employee base to be preselected when requesting a date for a course (Terminanfrage)
469 | Suffix Value not replicated
470 | "Search for actions or people" search bar not available;
471 | Payroll:Item:Permanent A/c No.
472 | HRS does not have direct reports to add pay targets
473 | Target LM notification
474 | The Position Cluster is just displaying a dash
475 | Workflow is not Generating
476 | unable to enter any values in 'New Target Total Direct Compensation'
477 | iled 50 and 51 of record type 1
478 | SIT3 - WFA_Day2_T0090_leaveOfAbsenceStartDate
479 | Testcase: Login as Linemanager instead of Employee
480 | Amex Concur - Corporate Address- not displaying address from FO only for AMOSA Entiy. For all other enttiies its displaying correctly.
481 | FMInteract - The translation rule is not working properly for the field 'Payroll_ID'
482 | ADP employee demographic rcipsoft
483 | Event Reason Drop Down - NO Data & Unable to edit Compensation Info
484 | LMS: REPORT Error
485 | ServiceNow UI - The fields which are mentioned as "Do not display in the SN form" could be removed from the requirement excel
486 | LTI_AZL_14-01-108_EC_OB_HRReporting_WFA_Day1_T0108_custom-string1
487 | Replizierung aufgrund ausgelöster PeCoSys-Meldung nicht möglich
488 | "Budget increase" window apperas but all amounts equal 0, so that no increase is possible.
489 | INT010_VolunteerMatch_Phone Number mapping change
490 | APPTIO : Expatriates should be excluded in the interface file, as per the requirement. But they are present in the file. - File used. ECPth_Apptio_20170915113441
491 | OrgChart UI - Name: Not displaying correct values in org chart UI and the visio diagram. Existing CR already present for this,
492 | There is no field "Record Completions" below the "Action" section
493 | SAPe Recruiting - The SAPeRecruiting interface file is pulling the records to interface file based on the selection criteria + the required fields. No error report has been generated.
494 | Admin Center not available
495 | INT032_Sailpoint_mapping change for the preferred name
496 | EC_OB_ECPth_AZLAD - Email address is mandatory and it causes many records to be moved to error report
497 | Please check Description of Testcase
498 | Verify new role expiry feature
499 | MFT : Additional files are sent in MFT with incorrect format, as per chris meyer. Look more in Actual result section.
500 | rcipsoft no salary related data in file
501 | Verify the cheque credit process is as expected
502 | LMS: The option/button "Email when Complete" is not available in any of the available Reports.
503 | AZLAD - File is not found in the MFT Inbound location, but received error report for two consecutive days.
504 | WFA_Day1_T0049_company - Global Company is not mapped
505 | LTI_AZL_11-02-10_EC_OB_Sailpoint - Manager emplid is by default pulling person-id-external
506 | Anlage einer Maßnahme in SAP ist falsch
507 | SIT TC: Unsinniger Testfall - Keine Mitarbeiterkreispflege über Unternehmensinformation möglich
508 | Please check Cancelation and Pricing Policies
509 | Service Now UI " Word Position is spelled incorrectly"
510 | Kundenindividueller Status Vorruhestand fehlt in SAP
511 | Warning Message
512 | SIT3 - WFA_Day2_T0280_referral_external_name
513 | SIT3 - WFA_Day2_T0284_variable_comp_start-date
514 | Only 2 reports show up - not five
515 | SIT2-EC-OB-SAP eRecruiting Employee1-Header record-First name and Last name doesn't have space inbetween
516 | Quality Resource Group(QRG) - inpatriate records are not pulled in the interface. (Note: sample records attached in actual result section)
517 | ServiceNow UI - Compensation team member is not able to view position request tasks assigned to the team
518 | SIT3 - WFA_Day2_T0250_externalCode
519 | Translain Last Name
520 | no Manager choice
521 | No Notification mail sent to the employee
522 | Approval Tasks that are DECLINED / REJECTED via email using Good Declines the Task, but does not Cancel the PR
523 | Can't select employee
524 | Gaps in test scenario description?
525 | Item Creation: validation error
526 | INT007_Quality_Resource_Group_Phone Number mapping change
527 | ServiceNow UI - Unable to change the status of the form when filled before close completing the task.
528 | HR WFA - WFA_Day1_T0093_manager-category is not working
529 | Script Error - LM vs HRS
530 | LTI_AZL_14-01-116_EC_OB_HRReporting_WFA_Day1_T0116_rel-user-id
531 | Verify the system settings parameters
532 | LTI_AZL_03_ServiceNow_T0002_UserInterface - Conflicting messages on ServiceNow when deleting job descr. / attachments after a user Submits on first page
533 | Enriched: Cybershift Userprofile :FOR Employee Belongs To Record : Record ending position shifted by one. Record ending position show as 107 instead of 106.
534 | INT010_VolunteerMatch_Terminated Employee Logic change
535 | Verify that user is able to create claims
536 | ADP demo file rcipsoft
537 | all
538 | LTI_AZL_26-02_20_EC_OB_SendWordNow_Day2_T0020_PHONE COUNTRY CODE 1 - this custom field is not following the business rule & not populating correctly
539 | There is no field for Interim Grade
540 | HRDW_MAIN.JOB_INFO: FIR_AND_PROPER should be FIT_AND_PROPER
541 | CoE-38cWithinDepartmentGrade13to15_Approval - Request for Geraldine Green Not in Pending Requests
542 | Search is selective for language
543 | System notification for Disability status change
544 | SAP eRecruit - Header 'BIRTHDATE' is missing in the FS but present in the file.
545 | Usability - Catalog Search - Filters
546 | Group requirements cannot be selected
547 | INT016-AZSE Active Directory "Personalid" mapped to payrollid field marked as Required. Non-Employee dont have Custom-string9, records move into error report.
548 | AZL Integration - Apptio Integration CR - Header name change
549 | ServiceNow UI - Comp team member is able to 'Assign Recruiter'. It is expected that only Tracy should be able to assign recruiter.
550 | HRS approval workflow notification not trigger for change disability
551 | LTI_AZL_14-01-117_EC_OB_HRReporting_WFA_Day1_T0117_card-type
552 | Verify SQL injection is not happening
553 | SIT2-EC-OB-HR WFA-(B) Is Primary: Getting False value even though Business Email is present and its primary.
554 | SF LMS CR Translations
555 | Copy of an SO had different amount of days than the original
556 | Updates in HCM do not reach SF LMS
557 | SIT3 - WFA_Day2_T0249_description
558 | No Notification received for HRS for ChangeDisabilityStatus
559 | Employee - RBP - Position Org Chart Visability - Please update script
560 | Org Chart UI -AZL Network ID should display all CAPITALS and "Type" field should display "Non-Employee" for Non-employee
561 | SIT2-DVFS-Selection Criteria: Only Active records are coming in file. Requirement clarification needed
562 | Modified eMail address is rejected during Feeder processing
563 | HRS 63A: Add Non-Employee Referral Code to Non-Employee Record
564 | LM is not able to change direct report's employment details
565 | Payroll:Item:Grade Code
566 | Test to verify sales user authorisation
567 | 01-04-29 No Workflow Recieved on this Saved Transaction from (01-04-28)
568 | EC_OB_ECPth_AZLAD - lot of records in the error report since Manager field is marked as 'required'